## hcy
Figure 3. Gantt Chart | Member | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Recruiting the PhD S. & Postdoc (open call)
WP1: Material Characterisation | bar: 2026 Q1 to 2026 Q4
T1.1 Alloy identification | PhD S. | bar: 2026 Q1 to 2026 Q2
T1.2 Strain-controlled cyclic testing | PhD S. | bar: 2026 Q3 to 2026 Q4
WP2: Analyses on Cracks | bar: 2027 Q1 to 2027 Q4
T2.1 Fatigue crack growth testing | PhD S. | bar: 2027 Q1 to 2027 Q4
T2.2 Interim residual stress study | PhD S. | bar: 2027 Q2 to 2027 Q4
WP3: Microstructure Investigation | bar: 2028 Q1 to 2028 Q4
T3.1 Residual stress investigations | PhD S. | bar: 2028 Q1 to 2028 Q4
T3.2 Grain orientation and texture analysis | Postdoc | bar: 2028 Q2 to 2028 Q4
T3.3 Temperature effect study | Postdoc | bar: 2028 Q4
WP4: Integration and Simulator Development | bar: 2028 Q3 to 2029 Q4
T4.1 Integration analysis | PhD S. | bar: 2028 Q3 to 2028 Q4
T4.2 Simulator development | Postdoc | bar: 2029 Q1 to 2029 Q4
Abb.: T: Task, M: Milestones, J: Journal paper, C: Conference paper, TW: Thesis writing, V: Research visit at The University of Tennessee